## Task_Table
S.No | Task Name | Status | Start | Finish | Comments/Questions
1 | Establish Access
2 | VPN | Completed | 2015-09-01 | 2015-09-01
3 | TestRail | Completed | 2015-09-01 | 2015-09-01
4 | JIRA | Completed | 2015-09-01 | 2015-09-01
5 | JIRA Project | Completed | 2015-09-01 | 2015-09-01
6 | Smartsheet | N/A |  |  | This is a project management tool. So I guess team do not need access to it
7 | DFP Sandbox | N/A
8 | DFP Sandbox API | N/A
9 | GIT Repository | Completed | 2015-08-28 | 2015-08-28
10 | Server for Control DB | N/A
11 | Jenkins | YTS |  |  | Yet to start
12 | Jenkins Slaves | YTS |  |  | Yet to start
13 | Test iPhone (accessible via Jenkins) - | N/A
14 | iPhone Source Code | Inprogress | 2015-09-14 |  | Need permissions to download the certificate so that we can compile a build. Monocept developers are looking in to it.
15 | Existing iPhone Automation Code | N/A
16 | Android Source Code | N/A
17 | Existing Android Automation Code | Completed
18 | Hockeyapp access | Completed | 2015-09-01 | 2015-09-16 | Access provided to iPOD Touch
19 | Static Code Analysis | YTS |  |  | Need to research on any free tools which does this
Planning
20 | High Level Project Plan | Completed | 2015-09-14 | 2015-09-15 | This is the draft version
21 | Solution Overview | Completed | 2015-09-14 | 2015-09-18 | All the required details are captured under ATP-961
22 | Automation Strategy | Completed | 2015-09-14 | 2015-09-18 | All the required details are captured under ATP-961
23 | Gain Approvals | Completed |  |  | I guess all the approvals in place to start the project.
24 | Setup Backlog in JIRA | Completed | 2015-09-01 | 2015-09-01
| Establish Initial Test Environment | In progress | 2015-09-16 |  | All the required details are captured under ATP-971
25 | Run one test end to end | In progress | 2015-09-16
| Onboard / Ramp Initial Team | In progress | 2015-09-01
26 | Knowledge Transfer | In progress | 2015-09-01 |  | Knowledge transfer is pending, as there are still lot of grey areas of understanding of the product
Automate Smoke Tests
27 | Select and understand Tests | Completed | 2015-09-14 | 2015-09-18
28 | Execute Test Manually | Completed | 2015-09-17 | 2015-09-18
29 | Automate DFP Campaing Creation | N/A |  |  | DFP is presently Out of Scope for this automation project
30 | Automate DFP statistics check | N/A
31 | Automate DFP Campaign cleanup | N/A
32 | Design framework for custom parameters | Completed | 2015-09-14 | 2015-09-18 | Video of the demo is shared with the stakeholders.
33 | Automating smoke tests | In progress | 2015-09-21
34 | Automating viewing ads in simulator | YTS
35 | Automate collecting viewing data from proxy in simulator | YTS
36 | Automate Clicking Ads in iphone in simulator | YTS
37 | Automate viewing ads in iphone | YTS
38 | Automate collecting viewing data from proxy | YTS
39 | Automate Clicking Ads in iphone | YTS
40 | Automate collecting clicking data from proxy | YTS
41 | Automate Data verification | YTS
42 | Create Basic Report | YTS
43 | Reporting via Dashboard | YTS |  |  | To receive mockups on reporting area.
44 | Automating regression tests in iphone
45 | Automating custom parameters in iphone
| Integrate with Jenkins | YTS |  |  | All the required details are captured under ATP-972
46 | Create Job to Execute DFPP Campaign Creation | YTS
47 | Create Job to Deploy and Start Proxy | YTS
48 | Create Job to Deploy iPhone application | YTS
49 | Create Job to Execute iPhone Test | YTS
50 | Create Job to Execute DFP Statistics Check | YTS
51 | Create Job to Execute DFP Campaign Creation Cleanup | YTS
52 | Create Job to validate Results and Generate Report | YTS
53 | Add Latency Allowances | YTS
54 | Chain Jobs
| End to End Automation | YTS
55 | iPhone | YTS
56 | Select Additional iPhone Tests | YTS
57 | Understand and Execute iPhone Tests Manually | YTS
55 | Automate DFPP Portions of iPhone Tests | N/A |  |  | DFPP and Product portions of iPhone Tests will be picked at a later stage of the project. Marking it as N/A asof now as no information is provided.
58 | Automate Proxy Portions of iPhone Tests | YTS
57 | Automate Product Portions of iPhone Tests | N/A
| Establish Dedicated Test Environment | YTS |  |  | All the required details are captured under ATP-971
59 | Setup Separate Application Environment | YTS
60 | Establish the ability to Mock Data | YTS
| Jenkins Integrations/Enhanced Reporting | YTS
61 | Integrate Tests with Jenkins as they're completed | YTS
62 | Enhance reporting/ provide dashboards | YTS
| Optimize and Grow | YTS
63 | Automate Operative | YTS |  |  | Optimization and Maintenance of the scripts will be at a very later stage of the project, once all the scripts are stable and running successufully seamlessly.
64 | Automate Adjuster | YTS
65 | Automate weather.com | YTS
66 | Automate m.weather.com | YTS
67 | Automate iPAD Application | YTS
68 | Automate Android Tablet application | YTS
69 | Automate Windows Phone | YTS
| Maintenance | YTS
70 | Maintain existing scripts | YTS
71 | Grow suite | YTS